## Dashboard
COLD STORAGE PROJECT - DPR DASHBOARD
Report Date: | 2026-07-07
Overall Project % |  | Total Activities |  | Rooms Ready for Handover | Total Rooms Tracked
88.73% |  | 118 |  | 0 | 7
ROOM-WISE HANDOVER STATUS
Room | PUF % | Door % | Floor % | Overall % | Planned Handover | Status
Ambient | 88.73% | 0% | 0% | 29.58% | 2026-07-10 | In Progress
Chiller | 0% | 0% | 0% | 0% |  | Not Started
Freezer | 0% | 0% | 0% | 0% |  | Not Started
Blast | 0% | 0% | 0% | 0% |  | Not Started
FNV | 0% | 0% | 0% | 0% |  | Not Started
Corridor & Warm Room | 0% | 0% | 0% | 0% |  | Not Started
Ante Room | 0% | 0% | 0% | 0% |  | Not Started
PLANT-WIDE WORK (Refrigeration / Electrical)
Category | % Complete
Refrigeration | 0%
Electrical | 0%

## Daily_Entry
DAILY PROGRESS ENTRY (fill this every day - one row per activity)
Instructions: Add a new row for every activity completed today. Select Room, Category & Item from the dropdown; enter today's quantity only (not cumulative). Every room sheet updates automatically.
Date | Room | Category | Item / Activity | UOM | Qty Done Today | Labour / Team | Remarks
2026-06-11 | Ambient | PUF Panel | Front Wall | Sq.m | 90 | Team A | Initial fixing started
2026-06-12 | Ambient | PUF Panel | Front Wall | Sq.m | 75 | Team A
2026-06-13 | Chiller | PUF Panel | Front Wall | Sq.m | 36 | Team A | 201 sq.m done till date, 12 pending
2026-07-07 | Ambient | PUF Panel | Back Wall | sq.m | 55 | farr
2026-06-14 | Freezer | Refrigeration | Refrigeration Piping | Sq.m | 10 | Rehman

## Ambient Room
AMBIENT ROOM - SCOPE & PROGRESS TRACKER
Room Overall % Complete: |  |  | 88.73% | Planned Handover Date: |  | 2026-07-10 | Status: | Near Completion
S.No | Category | Item / Activity | UOM | Target Qty | Planned Start | Planned Finish | Planned Handover | Cumulative Qty Done | % Complete | Balance Qty | Last Updated | Status | Remarks
1 | PUF Panel | Front Wall | Sq.m | 213 | 2026-06-26 | 2026-07-08 | 2026-07-10 | 165 | 77.46% | 48 | 2026-06-12 | In Progress
2 | PUF Panel | Back Wall | Sq.m | 200 |  |  |  | 200 | 100% | 0 | 2026-07-07 | Completed
3 | PUF Panel | Left Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
4 | PUF Panel | Right Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
5 | PUF Panel | Top Ceiling | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
6 | PUF Panel | PUF Slab (Floor) | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
7 | PUF Panel | Door Cutting | Nos |  |  |  |  | 0 |  |  |  | Not Started
8 | PUF Panel | Silicon Filling - Inside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
9 | PUF Panel | Silicon Filling - Outside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
10 | Door Work | Door Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
11 | Door Work | Falcon Sensor Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
12 | Door Work | Air Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
13 | Door Work | PVC Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
14 | Door Work | Door Alarm & Hooter Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
15 | Floor & Racking | Floor & Racking Work | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
Formulas:
Last Updated = IF(MAXIFS(Daily_Entry!$A5:A1000,Daily_Entry!$B5:B1000,"Ambient",Daily_Entry!$D5:D1000,[Item / Activity])=0,"",MAXIFS(Daily_Entry!$A5:A1000,Daily_Entry!$B5:B1000,"Ambient",Daily_Entry!$D5:D1000,[Item / Activity]))

## Chiller Room
CHILLER ROOM - SCOPE & PROGRESS TRACKER
Room Overall % Complete: |  |  | 0% | Planned Handover Date: |  |  | Status: | Not Started
S.No | Category | Item / Activity | UOM | Target Qty | Planned Start | Planned Finish | Planned Handover | Cumulative Qty Done | % Complete | Balance Qty | Last Updated | Status | Remarks
1 | PUF Panel | Front Wall | Sq.m |  |  |  |  | 36 |  |  | 2026-06-13 | In Progress
2 | PUF Panel | Back Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
3 | PUF Panel | Left Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
4 | PUF Panel | Right Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
5 | PUF Panel | Top Ceiling | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
6 | PUF Panel | PUF Slab (Floor) | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
7 | PUF Panel | Door Cutting | Nos |  |  |  |  | 0 |  |  |  | Not Started
8 | PUF Panel | Silicon Filling - Inside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
9 | PUF Panel | Silicon Filling - Outside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
10 | Door Work | Door Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
11 | Door Work | Falcon Sensor Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
12 | Door Work | Air Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
13 | Door Work | PVC Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
14 | Door Work | Door Alarm & Hooter Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
15 | Floor & Racking | Floor & Racking Work | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
Formulas:
Last Updated = IF(MAXIFS(Daily_Entry!$A5:A1000,Daily_Entry!$B5:B1000,"Chiller",Daily_Entry!$D5:D1000,[Item / Activity])=0,"",MAXIFS(Daily_Entry!$A5:A1000,Daily_Entry!$B5:B1000,"Chiller",Daily_Entry!$D5:D1000,[Item / Activity]))

## Freezer Room
FREEZER ROOM - SCOPE & PROGRESS TRACKER
Room Overall % Complete: |  |  | 0% | Planned Handover Date: |  |  | Status: | Not Started
S.No | Category | Item / Activity | UOM | Target Qty | Planned Start | Planned Finish | Planned Handover | Cumulative Qty Done | % Complete | Balance Qty | Last Updated | Status | Remarks
1 | PUF Panel | Front Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
2 | PUF Panel | Back Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
3 | PUF Panel | Left Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
4 | PUF Panel | Right Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
5 | PUF Panel | Top Ceiling | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
6 | PUF Panel | PUF Slab (Floor) | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
7 | PUF Panel | Door Cutting | Nos |  |  |  |  | 0 |  |  |  | Not Started
8 | PUF Panel | Silicon Filling - Inside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
9 | PUF Panel | Silicon Filling - Outside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
10 | Door Work | Door Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
11 | Door Work | Falcon Sensor Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
12 | Door Work | Air Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
13 | Door Work | PVC Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
14 | Door Work | Door Alarm & Hooter Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
15 | Floor & Racking | Floor & Racking Work | Sq.m |  |  |  |  | 0 |  |  |  | Not Started

## Blast Room
BLAST ROOM - SCOPE & PROGRESS TRACKER
Room Overall % Complete: |  |  | 0% | Planned Handover Date: |  |  | Status: | Not Started
S.No | Category | Item / Activity | UOM | Target Qty | Planned Start | Planned Finish | Planned Handover | Cumulative Qty Done | % Complete | Balance Qty | Last Updated | Status | Remarks
1 | PUF Panel | Front Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
2 | PUF Panel | Back Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
3 | PUF Panel | Left Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
4 | PUF Panel | Right Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
5 | PUF Panel | Top Ceiling | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
6 | PUF Panel | PUF Slab (Floor) | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
7 | PUF Panel | Door Cutting | Nos |  |  |  |  | 0 |  |  |  | Not Started
8 | PUF Panel | Silicon Filling - Inside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
9 | PUF Panel | Silicon Filling - Outside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
10 | Door Work | Door Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
11 | Door Work | Falcon Sensor Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
12 | Door Work | Air Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
13 | Door Work | PVC Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
14 | Door Work | Door Alarm & Hooter Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
15 | Floor & Racking | Floor & Racking Work | Sq.m |  |  |  |  | 0 |  |  |  | Not Started

## FNV Room
FNV ROOM - SCOPE & PROGRESS TRACKER
Room Overall % Complete: |  |  | 0% | Planned Handover Date: |  |  | Status: | Not Started
S.No | Category | Item / Activity | UOM | Target Qty | Planned Start | Planned Finish | Planned Handover | Cumulative Qty Done | % Complete | Balance Qty | Last Updated | Status | Remarks
1 | PUF Panel | Front Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
2 | PUF Panel | Back Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
3 | PUF Panel | Left Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
4 | PUF Panel | Right Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
5 | PUF Panel | Top Ceiling | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
6 | PUF Panel | PUF Slab (Floor) | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
7 | PUF Panel | Door Cutting | Nos |  |  |  |  | 0 |  |  |  | Not Started
8 | PUF Panel | Silicon Filling - Inside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
9 | PUF Panel | Silicon Filling - Outside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
10 | Door Work | Door Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
11 | Door Work | Falcon Sensor Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
12 | Door Work | Air Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
13 | Door Work | PVC Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
14 | Door Work | Door Alarm & Hooter Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
15 | Floor & Racking | Floor & Racking Work | Sq.m |  |  |  |  | 0 |  |  |  | Not Started

## Corridor & Warm Room
CORRIDOR & WARM ROOM - SCOPE & PROGRESS TRACKER
Room Overall % Complete: |  |  | 0% | Planned Handover Date: |  |  | Status: | Not Started
S.No | Category | Item / Activity | UOM | Target Qty | Planned Start | Planned Finish | Planned Handover | Cumulative Qty Done | % Complete | Balance Qty | Last Updated | Status | Remarks
1 | PUF Panel | Front Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
2 | PUF Panel | Back Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
3 | PUF Panel | Left Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
4 | PUF Panel | Right Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
5 | PUF Panel | Top Ceiling | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
6 | PUF Panel | PUF Slab (Floor) | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
7 | PUF Panel | Door Cutting | Nos |  |  |  |  | 0 |  |  |  | Not Started
8 | PUF Panel | Silicon Filling - Inside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
9 | PUF Panel | Silicon Filling - Outside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
10 | Door Work | Door Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
11 | Door Work | Falcon Sensor Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
12 | Door Work | Air Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
13 | Door Work | PVC Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
14 | Door Work | Door Alarm & Hooter Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
15 | Floor & Racking | Floor & Racking Work | Sq.m |  |  |  |  | 0 |  |  |  | Not Started

## Ante Room
ANTE ROOM - SCOPE & PROGRESS TRACKER
Room Overall % Complete: |  |  | 0% | Planned Handover Date: |  |  | Status: | Not Started
S.No | Category | Item / Activity | UOM | Target Qty | Planned Start | Planned Finish | Planned Handover | Cumulative Qty Done | % Complete | Balance Qty | Last Updated | Status | Remarks
1 | PUF Panel | Front Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
2 | PUF Panel | Back Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
3 | PUF Panel | Left Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
4 | PUF Panel | Right Side Wall | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
5 | PUF Panel | Top Ceiling | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
6 | PUF Panel | PUF Slab (Floor) | Sq.m |  |  |  |  | 0 |  |  |  | Not Started
7 | PUF Panel | Door Cutting | Nos |  |  |  |  | 0 |  |  |  | Not Started
8 | PUF Panel | Silicon Filling - Inside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
9 | PUF Panel | Silicon Filling - Outside | Rmt |  |  |  |  | 0 |  |  |  | Not Started
10 | Door Work | Door Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
11 | Door Work | Falcon Sensor Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
12 | Door Work | Air Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
13 | Door Work | PVC Curtain Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
14 | Door Work | Door Alarm & Hooter Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
15 | Floor & Racking | Floor & Racking Work | Sq.m |  |  |  |  | 0 |  |  |  | Not Started

## Common_Works
COMMON WORKS (REFRIGERATION & ELECTRICAL) - SCOPE & PROGRESS TRACKER
S.No | Category | Item / Activity | UOM | Target Qty | Planned Start | Planned Finish | Planned Handover | Cumulative Qty Done | % Complete | Balance Qty | Last Updated | Status | Remarks
1 | Refrigeration | ODU Hanging | Nos |  |  |  |  | 0 |  |  |  | Not Started
2 | Refrigeration | ODU MS Structure | Nos |  |  |  |  | 0 |  |  |  | Not Started
3 | Refrigeration | Refrigeration Piping | Rmt |  |  |  |  | 0 |  |  |  | Not Started
4 | Refrigeration | GI Cable | Rmt |  |  |  |  | 0 |  |  |  | Not Started
5 | Refrigeration | Drain Piping | Rmt |  |  |  |  | 0 |  |  |  | Not Started
6 | Refrigeration | IDU Hanging | Nos |  |  |  |  | 0 |  |  |  | Not Started
7 | Refrigeration | IDU Connection | Nos |  |  |  |  | 0 |  |  |  | Not Started
8 | Refrigeration | Control Panel Installation | Nos |  |  |  |  | 0 |  |  |  | Not Started
9 | Refrigeration | Nitrogen Holding | Job |  |  |  |  | 0 |  |  |  | Not Started
10 | Refrigeration | Vacuum Pressure Test | Job |  |  |  |  | 0 |  |  |  | Not Started
11 | Refrigeration | Machine Start | Job |  |  |  |  | 0 |  |  |  | Not Started
12 | Electrical | Copper FRLS Cable Laying | Rmt |  |  |  |  | 0 |  |  |  | Not Started
13 | Electrical | Final Handover to Client | Job |  |  |  |  | 0 |  |  |  | Not Started

## Room_Handover
ROOM-WISE PROGRESS & HANDOVER TRACKER
Room | PUF Panel % | Door Work % | Floor & Racking % | Overall Room % | Planned Handover Date | Actual Handover Date | Delay (Days) | Handover Status | Remarks
Ambient | 88.73% | 0% | 0% | 29.58% | 2026-07-10 | 2026-07-07 | -3 | In Progress
Chiller | 0% | 0% | 0% | 0% |  |  |  | Not Started
Freezer | 0% | 0% | 0% | 0% |  |  |  | Not Started
Blast | 0% | 0% | 0% | 0% |  |  |  | Not Started
FNV | 0% | 0% | 0% | 0% |  |  |  | Not Started
Corridor & Warm Room | 0% | 0% | 0% | 0% |  |  |  | Not Started
Ante Room | 0% | 0% | 0% | 0% |  |  |  | Not Started
PLANT-WIDE WORK (Refrigeration / Electrical / Handover)
Category | % Complete | Last Updated | Status
Refrigeration | 0% |  | Not Started
Electrical | 0% |  | Not Started
Formulas:
Delay (Days) = IF(AND([Planned Handover Date]<>"",[Actual Handover Date]<>""),[Actual Handover Date]-[Planned Handover Date],IF(AND([Planned Handover Date]<>"",TODAY()>[Planned Handover Date],[Overall Room %]<1),TODAY()-[Planned Handover Date],""))

## Milestones
KEY MILESTONE DATES
Room / Milestone | Committed Date - Vendor | FKI (Freeze Date) | Actual Date | Delay (Days)
Ambient | 2026-05-06 | 7th
Chiller | 2026-05-10 | 10th
Freezer | 2026-05-16 | 16th
Blast | 2026-05-17 | 18th
FNV
Corridor & Warm Room | 2026-05-18 | 19th
Ante Room
Refrigeration Piping Completion
Final Handover (HO)

## Lists (hidden)
Rooms | Categories | Items | Status
Ambient | PUF Panel | Air Curtain Installation | Not Started
Chiller | Door Work | Back Wall | In Progress
Freezer | Floor & Racking | Control Panel Installation | Completed
Blast | Refrigeration | Copper FRLS Cable Laying | Delayed
FNV | Electrical | Door Alarm & Hooter Installation
Corridor & Warm Room |  | Door Cutting
Ante Room |  | Door Installation
Common / Plant-wide |  | Drain Piping
Falcon Sensor Installation
Final Handover to Client
Floor & Racking Work
Front Wall
GI Cable
IDU Connection
IDU Hanging
Left Side Wall
Machine Start
Nitrogen Holding
ODU Hanging
ODU MS Structure
PUF Slab (Floor)
PVC Curtain Installation
Refrigeration Piping
Right Side Wall
Silicon Filling - Inside
Silicon Filling - Outside
Top Ceiling
Vacuum Pressure Test